Wexford County Council

2018

Annual Service Delivery Plan

TABLE of CONTENTS

Strategic Capital Projects							Page 1 - 2

Human Resources									Page 3 - 4

Corporate Affairs									Page 5 - 6

Communications									Page 6

Facilities										Page 7

Economic Development								Page 8 - 9

Tourism										Page 10 - 11

Planning										Page 12 - 13

Finance										Page 14 - 15

Information & Communication Technology (ICT)				Page 16 - 17

Libraries & Archives								Page 18

Arts											Page 19 – 20 - 21

Housing										Page 22

Environment									Page 23

Community										Page 24 - 28

Sports Active Wexford								Page 29 - 50

Fire Service	 / Civil Defence							Page 51

Roads & Transportation								Page 52 - 54

Water Services									Page 55 - 56

Health & Safety									Page 57 - 58

CAPITAL DEVELOPMENT HR & CORPORATE SERVICES

Delivery of Strategic Capital Projects

| STRATEGIC CAPITAL PROJECTS | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Progress Planning and Development of Trinity Wharf and Wexford Quay Projects | STW appointed to prepare master plan, EIA and planning consent application. | Draft Master plan to be completed by end of June. Environmental Impact assessment processes have commenced and are to be completed by September 2018. Application to ABP to be submitted in October 2018 | Master plan approaching Completion and put on Public Display in September. Part 8 process for refurbishment of Crescent Quay Commenced in September | Application for planning approval for Trinity Wharf submitted to An Bord Planeala. Contractor appointed to Crescent Quay redevelopment |
| Secure Planning Approval and commence Construction of Site Services for Enniscorthy Technology Park | Part 8 Planning application public consultation processes completed in Q1 with report to Council to be presented to Council at the May 2018 meeting. | Planning consent for the development was granted by WCC at the May meeting. Tenders for the construction works are currently being evaluated and it is planned to award the contract for construction works in July 2018. | Construction Commenced on Phase 1 of Access Road and Services in August | Planning Phase Complete and Construction commenced and scheduled for completion in Q1 2019. |
| Commence and Complete Construction of Min Ryan Park in Wexford | Tenders for construction of the Park received in Q1 2018. Tender review processes underway. | Following a detailed tender assessment process, the preferred tender was withdrawn and the contract has been re-tendered. Closing dates for tenders is 26th June 2018. A contract is expected to be awarded by mid-August and works are expected to commence on site in September 2018. | Tendering Process for Contractor concluded with Appointment of Contractor and Commencement on Site in September | Construction Commenced and Park scheduled for Completion n Q3 2019. |
| Commence and Complete Construction of Gorey Town & District Park. | Tenders have been received and are being assessed. | Check with A Byrne, Gorey District Manager | Project undergoing Re-tendering due to unsuccessful first tendering process. | Tenders for Construction being assessed and construction scheduled to commence in Q1 2019. |
| Procure and Establish a Consultants Framework to ensure efficient delivery of Capital Projects across Organisation | Tendering Process for Architectural, Bridge and Civil Engineering Consultants underway. Submissions being assessed and Framework to be in place in Q2. | All tenders are in for Architectural, Bridge and Civil Engineering Consultants Framework. 3 Evaluation boards currently being set up and evaluation’s to start at end of July. | Frameworks for Road, Bridge and Architectural Consultants (broken into lots based on project sizes) in place | Complete - Framework, for Engineering and Architectural Consultants established. |
| Progress Strategic Development projects in accordance with agreed Programmes | Project Management system for capital projects agreed | Project Management system for capital projects in place. | Project management System in Place and Projects being progressed according to Programme | Development of Projects progressing in accordance with Programme |
| Develop a pipeline of Greenway projects for the County. | Feasibility study for greenways from Rosslare to Waterford commenced in Q1.Part 8 planning documents for the New Ross Red Bridge substantially completed. | Rosslare to Waterford Greenway Project is running on programme with initial environmental studies and investigative works in progress. Draft route selection reports and environmental screening documents are to be completed by end of July. New Ross Redbridge Greenway is currently in Part 8 planning stage with submissions and observations due by 17th July. South East Regional Strategy A brief for services has been completed and agreement to proceed to procurement is currently under review. | Part 8 Approval secured for Waterford to Mountelliot Section. Tenders for detailed design for this section being sought by WCC. Draft Feasibility Report on Rosslare to Waterford being reviewed and due for publication in October | Consultants for Detailed Design of Waterford to New Ross/Mountelliot Greenway being appointed. Feasibility report on Rosslare to Waterford Greenway finalised and planning application to be made in Q2 2019. |

Support Staff Development and Performance through the implementation of Best Practise in Human Resource Management

| HUMAN RESOURCES | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Develop and embed PMDS throughout Local Authority | Initial meeting held with HR and LGMA. | Working group has been established. | List of Team Development Plans Agreed and Format of TDP’s to be agreed in September | Team Development Plans being finalised |
| Develop a Best Practice HRM Strategy and lead its implementation | At research stage. | National template nearing completion. | Main Contents and objectives of Strategy Agreed - will be completed in accordance with National Strategy | National ‘People Strategy’ framework launched - 3 key priorities identified for 2019 by Wexford CoCo with a number of secondary objectives also identified for progress. 2019-2022 Wexford HRM Strategy will follow framework of the national ‘People Strategy’. |
| Review and Update Content and Policies of Staff Handbook | Commenced – ongoing. | Ongoing | Review on going and will be complete by year end | Policy review ongoing – range of new policies identified and changes to existing proposed. Full set to be drafted for comment and consultation early in Q1 2019 |
| Develop and co-ordinate delivery of a Corporate Training and Development Plan to serve individual, departmental and corporate learning and development needs. | Analysis of Training Needs 80% complete. | Ongoing | 2018 Training Needs Analysis complete and associated training underway | Outdoor / Technical Training Needs Analysis Complete and training ongoing. Move to undertake Training Needs Analysis for indoor/administrative staff Q1 2019 |
| Conduct an annual review of the Workforce Plan to review critical vacancies, staff mobility needs and succession planning | In progress. | Initial meetings with Directors have been completed. Summary being prepared for management team. | Review of Indoor WFP Complete. Gap analysis and prioritisation ongoing. Critical Vacancies Identified and being filled | WFP 2019 complete and critical vacancies being filled. |
| Manage, co-ordinate and support the Attendance Management Plan and achievement of the public sector target of sick leave at 3.5%. | Ongoing | Ongoing. | On-going | Introduction of CORE adding support to the Attendance Management Plan and delivery of 3.5% sick leave target |
| Ensure effective Industrial Relations Structures & Practices | Ongoing | Ongoing- regular meetings held with the unions. | Regular Meetings being held with Union Officials and Workplace representatives | Regular engagement with Union Officials and Representatives. |

CORPORATE AFFAIRS

Support and enhance the democratic role of the Council, and the development, co-ordination and promotion of a Corporate Culture and Business Ethos

| CORPORATE AFFAIRS | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Finalise New Polling Scheme including a review of the role of Compilers & begin preparations for Local elections in 2019. | Polling scheme approved by Council at its March 2018 meeting | Completed Q1 | Complete | Complete |
| Review & Update the Councils Document Retention Policy | Convened meetings of Records Management Team, Commenced development of work programme. | Ongoing meeting of Records Management Team | On-going in conjunction with National Policy | Review of HR Document Retention Policy commenced |
| Comply with the requirements of GDPR | Audit of Council’s records in Q1. Acquired database to record nature and extent of all records held by the Council | Ongoing input to Database of Records Series | On-going. Database of records complete and Privacy Policies and procedures in place or imminent | Review of the legal basis for collection and retention of HR Records commenced |
| Prepare Plan a Procurement Plan to identify and centralise contracts for all corporate services to comply with Procurement and to gain efficiencies and cost savings across the organisation. | Procurement Plan agreed by management Team | Review all credit card spend with a view to reducing Credit limits; also update our Credit Card policy Document. Review carried out by G. P. on Office Water Supply, Furniture acquisition and Hygiene Products. | Credit Card (LVP) Review Complete and new limits and Policies in place. CCTV Costs being reviewed and savings identified. | Review of CCTV costs and savings complete. |
| Co-ordinate the identification and compilation of all local and national service indicators for reporting on our performance in corporate publications and communications as appropriate | Analysis of 2016 Performance Indicators being carried out for presentation to Council in Q2 | Presentation of NOAC Report. Targeted Performance Indicators presented to May meeting of WCC and also presented to the Audit Committee | Complete | Review of 2017 NOAC Report commenced. |
| Prepare all corporate publications including the Annual Service Delivery Plan and Annual Report | Annual Service Delivery Plans being prepared for presentation to Council in Q2. Draft of 2016 Annual Report to Council in Q2/Q3 Draft of 2017 Annual Report will be presented to Council in Q3 | Annual Service Delivery Plan approved by Council at the May Meeting of WCC. Draft of 2016 Annual Report to Council in Q2/Q3 Draft of 2017 Annual Report will be presented to Council in Q3 | ASDP and Quarterly reporting in place. 2016 Annual report Complete. 2017 Annual report to be presented to October Meeting. | Annual Reports for 2016 & 2017 complete. Annual Report 2018 commenced. Q4 Annual Service Delivery Plan 2018 in preparation. |
| Communicate effectively with customers and the public and promote a positive Corporate Image of the Local Authority | 55,000 copies of Economic and Community Investment Programme delivered countywide. Successfully Communicated with the public during Storm Emma using a wide range of media. |  | Customer Service Unit Established and website being updated continuously. Model Publication scheme for Website being devised. Regular Press releases being issued | Environment Customers now managed through CSU. Website and Twitter updated daily by CSU. Currently 10.000 followers on Twitter. Corporate email address now operational at customerservice@wexfordcoco.ie |

COMMUNICATIONS

Communicate effectively with customers and the public and promote a positive Corporate Image of the Local Authority

| COMMUNICATIONS | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Establish the Customer Service Unit and resource as required. | Project Team established CSU staff structure agreed and initial staff assigned Staff training programme designed Tenders received for provision of CRM system Design of CSU area complete - tenders sought for installation Staff Awareness programme initiated | Completed Continuing Staff Assignment Staff Training provided & will continue Tenders reviewed & Firmstep appointed to deliver CRM System CSU area now complete together with appropriate signage Continuing process | Completed Continuing Staff Assignment Staff Training provided & will continue Tenders reviewed & Firmstep appointed to deliver CRM System CSU area now complete together with appropriate signage Continuing process | Complete |
| Continue to Implement and embed the Councils Communications Strategy 2017-2020 | Complete as per end Q1 2018 | Complete as per end Q1 2018 | Complete as per end Q1 2018 | Complete |

FACILITIES

Manage the Operation and Maintenance of Corporate Buildings and Facilities

| FACILITIES | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Complete a review of all Staff Accommodation and develop a long term Facilities & Storage Management Strategy | Review Commenced and works commenced on New Wexford MBD in Bull Ring. Long Term Paper Storage Requirements have been ascertained. | Works on-going on Wexford MBD Offices. Review of Corporate Accommodation needs in Enniscorthy commenced. | Works on going in Wexford MBD. Corporate Estate Plan for Enniscorthy finalised and includes renovation of Courthouse and Market Square | Construction commenced on refurbishment of Enniscorthy Courthouse. Liaising with property management section ongoing regarding the potential of vacant council owned units for future storage space |
| In conjunction with Document retention Policy, develop a Storage Plan for Council Paper Records | Work on National Document/Record retention Policy on-going and partial adoption underway. Strategy of Phased Implementation to be formulated | Section by Section Audit of current Document retention and storage practices initiated. Confidential Shredding policy prepared and segregated paper waste /shredding facilities agreed and being put in place | Audit Completed of misc. Storage in Districts and plan being devised to centralise. Confidential shredding system in place. | Retention in each section in the context of GDPR being reviewed with support of GDPR team. HR in progress, other sections will be reviewed in 2019, which will release storage space. Work progressing on the review of the National Retention Policy with two sections approved and now ready for implementation.. |

ECONOMIC DEVELOPMENT & PLANNING

Economic Development

Maintain a supportive pro-business environment in County Wexford

| ECONOMIC DEVELOPMENT | Q2 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Continue to support and promote the LEOs extensive range of business supports to the start-up and micro-enterprises in the county via www.localenterprise.ie/Wexford | Programme of training and events agreed and being delivered across the County. | Programme of training and events agreed and being delivered across the County. Autumn Programme in Design Spring Training Programme 26 events 332 Participants 71 Mentor Assignments | Programme of training and events agreed and being delivered across the County. Autumn Training Programme (Sept to Dec) 44 training events organised; 79 Mentor Assignments to date Jan-Sept 2018 | The LEO programme of business training for 2018 is now complete. In summary 79 training events took place with 983 participants. The mentor programme received 108 applications with 214 mentor meetings conducted in 2018. |
| Continue to work with the four Chambers of Commerce and other business interest in the county to support a pro-business culture. | Wexford County Council is working with the Chambers in each location on a number of priority events and projects. Joint projects at a county level are also being considered during 2018. | Wexford County Council is working with the Chambers in each location on a number of priority events and projects. Joint projects at a county level are also being considered during 2018. | Wexford County Council is working with the Chambers in each location on a number of priority events and projects. Joint projects at a county level are also being considered during 2018. | The Economic Development Unit in Wexford County Council continues to work with the 4 Chambers of Commerce in County Wexford and other third parties on a number of events and projects. |
| Manage and promote FDI in conjunction with the IDA and Enterprise Ireland, particularly in relation to the M11 Business Campus in Gorey. | Ongoing promotion and marketing activities with EI and IDA in relation to incoming itineraries and business enquiries. Launch of the M11 Campus will take place on April 20th 2018. | Ongoing promotion and marketing activities with EI and IDA in relation to incoming itineraries and business enquiries. Launch of the M11 Campus took place April 20th and The Hatch Lab launched 8th June. | Ongoing promotion and marketing activities with EI and IDA in relation to incoming itineraries and business enquiries. A number of itineraries of new potential business to the M11 business campus have been facilitated | The Economic Development Unit continues to support both the IDA and Enterprise Ireland in their efforts to attract inward investment into County Wexford from foreign and domestically owned business. |
| In conjunction with the Special Projects Unit assist in the delivery of Economic Development Projects throughout the County. | Key projects in main towns are being progressed, including Enniscorthy Business Park, M11 Campus, New Ross ATB and Trinity Wharf. | Key projects in main towns are being progressed, including Enniscorthy Science and Technology Park, New Ross Advanced Technology Building and Trinity Wharf. | Key projects in main towns are being progressed, including Enniscorthy Technology Park, New Ross Advanced Technology Building and Trinity Wharf. Enniscorthy technology park is now under construction, with master planning underway for Trinity Wharf | The Enniscorthy Science and Technology Park is now under construction. Trinity Wharf is now Master Planned and due to be submitted for planning to An Bord Pleanala in early 2019. |

Support the Tourism Industry in County Wexford via the Visit Wexford Structure

| TOURISM | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Finalise and launch a new 5 year Tourism Strategy for County Wexford | Genesis consultants were commissioned to undertake the development of the new 5 year tourism strategy in June 2017. Desk-based research and consultation phases have now been complete. | Genesis consultants were commissioned to undertake the development of the new 5 year tourism strategy in June 2017. Desk-based research and consultation phases have now been complete. Strategy now at Drafting Stage. Expected completion 4th Quarter. | Genesis consultants were commissioned to undertake the development of the new 5 year tourism strategy in June 2017. Strategy now at second draft stage. Expected completion 4th Quarter. | The County Wexford Tourism Strategy is now at final draft stage and was presented to the SPC for Economic Development in Nov 2018. The Strategy will be presented to the full Council Chamber in early 2019 |
| Continue to promote and market Tourism in County Wexford via the Visit Wexford structures in association with the tourism industry in the county | A Marketing Plan, in conjunction with Visit Wexford Tourism, is being delivered, along with funding to a number of festivals and events across the County to help promote Wexford as top destination. | A Marketing Plan, in conjunction with Visit Wexford is being delivered, along with funding to a number of festivals and events across the County to help promote Wexford as top destination. A new summer campaign – Passport to Fun currently being rolled out. | A Marketing Plan, in conjunction with Visit Wexford is being delivered, along with funding to a number of festivals and events across the County to help promote Wexford as top destination. | A comprehensive marketing plan for Visit Wexford was delivered in 2018 via offline and online channels. Wexford County Council supported a number of festivals and events throughout a busy 2018. |
| Revise and re-launch the new www.visitwexford.ie website | Graphedia were commissioned in late 2017 to undertake a revamp of the Visit Wexford website. Initial redesign has been complete and the new look site will go live towards the end of April 2018. | Graphedia were commissioned in late 2017 to undertake a revamp of the Visit Wexford website. The new site went live end of May 2018. | Complete | Complete |

Continue to promote County Wexford as a great business investment opportunity via www.InvestWexford.ie

| Distribute the Our Wexford Magazine widely to the investment community as a showcase for investment opportunity in the county | 3rd Edition of magazine complete and distribution to 50% of targeted audience complete. | 3rd Edition of magazine complete and distribution to 50% of targeted audience complete. | 3rd Edition of magazine complete and distribution to 75% of targeted audience complete. | Completed |
| --- | --- | --- | --- | --- |
| Revise and re-launch the portal website www.wexford.ie as an online showcase for promotion of the county with extensive photography and video | Tender awarded with redesign and content copy complete. Portal site is expected to go live in 2nd quarter 2018. | Tender awarded to PixelPod for redesign and content copy. Slight delay in delivery with new site now expected to go live in 4th quarter 2018. | New site expected to go live in 4th quarter 2018. Draft site under review | The portal site www.wexford.ie is now launched and is live. The site is an online guide to County Wexford. An additional Wexford Ambassador (People) section will be added in early 2019 |

Support the delivery of the BUCANIER project in conjunction with project partners in Ireland and Wales

| Roll out the promotion of the www.bucanier.eu project throughout the county and the region. | Very successful Irish launch of Bucanier project delivered in March 2018, with over 100 people in attendance. Active promotion of the project underway with strong interest from SME’s across the Southern region. | Active promotion of the project underway with strong interest from SME’s across the Southern region from Wicklow to Kerry. | Signed up 26 companies between Irish partners, 16 directly signed by Wex Co Co. All companies assigned a mentor, project action plans for each company in process, ongoing recruitment of companies. | BUCANIER has now signed up 36 Irish Companies to participate on this program. All companies are now assigned a mentor and project actions being developed. |
| --- | --- | --- | --- | --- |

PLANNING

Ensure an effective, proper planning and sustainable, balanced development of urban and rural areas.

| PLANNING | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Continue the preparation of the Draft County Development Plan 2019-2025 in accordance with statutory timeframes. | Preparation ongoing Consultants appointed and work commenced on Retail Strategy, Housing Strategy and SEA | Work continues on retail and housing strategies. SEA continues to be amended. Flood mapping has been received, Support work to RSES PROGRESSING. Progress of Plan halted until adoption of RSES. | Work continues on retail and housing strategies and plan chapters and RPS. SEA continues to be amended. Statutory processes suspended under 2018 Act pending finalisation of RSES. Initial support work to RSES completed. | Work continues on retail and housing strategies and plan chapters and RPS. Statutory processes suspended under 2018 Act pending finalisation of RSES. Initial support work to RSES completed. |
| Review the Wexford Town and Environs Development Plan and prepare a new plan for the Area. | Review may be delayed until RSES ADOPTED | Commencement of Review delayed until adoption of RSES which will determine population and required zoning | Work progressing on the procurement of consultants (SEA/AA/SFRA) and desk and field based research. Statutory processes suspended under 2018 Act pending finalisation of RSES. | Work progressing on the procurement of consultants (SEA/AA/SFRA) and desk and field based research. Statutory processes suspended under 2018 Act pending finalisation of RSES. Work ongoing on preparation of Pre-Draft L.A.P. |
| Maintain a Vacant Site Register in accordance with the Urban Housing and Regeneration Act 2015. | 3 sites on register further assessments to be carried out | Notices issued for levy as required. | Consider New sites for inclusion on vacant sites register Enniscorthy and New Ross | Initial capture of potential sites completed |
| Continue to proactively manage planning enforcement cases and reduce the number of open enforcement files. | Ongoing assessment and management of Enforcement Files | Cases resolved 142 Cases opened 83. | Progress Enforcement in Building Control | Enforcement of Building Control case with Law agent for prosecution |
| Ensure measures contained in “Rebuilding Ireland” relating to development management are implemented. | Preplanning committee established to prioritise housing estate planning applications. Processing of SHD`S with ABP ongoing | Preplanning committee established to prioritise housing estate planning applications. Processing of SHD`S with ABP ongoing | Review identified cases on Short term Lettings. Assess impact of recent guidelines on Apartments & Granny Flats | Review on Short term Lettings ongoing. Review on Apartments & Granny Flat completed. |
| Maintain proactive preplanning support service and ensure target timelines are met for Preplanning for Residential Development. | Processes’ established and implemented – ongoing development | Number of major housing developments preplanning completed within 4 weeks: 15 | Review Pre Planning System on account of provisions of 2018 Act | Review Pre Planning System on account of provisions of 2018 Act |
| Implement the County Biodiversity Plan | GSI Report Completed | GSI Report Completed | Publication In Progress | Publication In Progress |
| Manage Roll out of the proposed National e-planning service portal. | Meetings with service provider. Timeline and Costings to be submitted | Upgrading of APAS to enable E-Planning has been scheduled. | Apas Upgrade installed. Currently in Testing Phase Scanning Tenders received and Scanning provider to be appointed. | Apas Upgrade installed and in service Scanning provider appointed. New document scanning protocol implemented. |

FINANCE & ICT

Provide robust financial management and risk management systems

| FINANCE | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Support and enhance cash flow, treasury management and financial management best practice within the organisation. | Ongoing | Ongoing | Ongoing | Completed for 2018 |
| Monitor and report on income and expenditure against budget for the 2018 Revenue budget and the 2018 capital programme. | Ongoing | Q2 Review commenced | Q2 Review completed | Completed for 2018 |
| Support and promote timely income billing, state and agency recoupment and enhanced debt management across the organisation. | Ongoing | Ongoing | Ongoing | Completed for 2018 |
| Facilitate and manage, in association with the Valuation Office, work on delivering the 2019 revaluation of all rateable properties in County Wexford as part of the national revaluation programme. | Ongoing | Progressing | Progressing | All 2018 phases of this objective are complete |
| Continue to strive to maximise the Rateable revision process to ensure all Rateable properties are referred to the Valuation office in a timely manner. | Ongoing | Ongoing | Ongoing | Completed for 2018 |
| Promote and support the core VFM principles of efficiency, effectiveness and economy in all corporate activities. | Ongoing | Ongoing | Ongoing | Completed for 2018 |

| Facilitate and manage the 2019 Budget Strategy consultation process including the LPT variation procedure. | To commence Q3 | Not commencing until Q3 | Almost completed | Complete |
| --- | --- | --- | --- | --- |
| Facilitate and deliver an adequate Revenue Budget for 2019 Operational Year. | To commence Q3 | Not commencing until Q3 | Detailed Work commenced | Complete |
| Work with Programme Managers to prepare and deliver a relevant Capital Programme Budget for 2018 – 2020 with associated funding requirements identified. | Complete | Completed Q1 | Ongoing | Work in progress. To be completed early 2019 |
| Prepare the 2017 annual accounts for audit in compliance with the prescribed format and the Local Authority Accounting in Ireland Code of Practice and Accounting Regulations. | Complete | Completed Q1 | Ongoing | Complete |
| To progress Core Payroll project with a view to implementation in 2019, providing support and training for staff in advance of implementation | Progressing | Stage 1 (Indoor Staff & Pensioners) Complete | Stage 2 (Coretime implementation now complete) Work progressing on integrating outdoor staff on Core System | All 2018 phases of this objective are complete |
| To review and plan for FMS Upgrade and associated business improvements and provide support & training for staff during and following implementation. | To commence Q2 | Discussions commenced with provider | Preliminary Discussions Ongoing | Work in progress. To be completed 2019. |
| Deliver the 2018 Audit Programme and support the Audit function including the Audit Committee, NOAC engagement and Public spending code reporting. | Ongoing | Progressing | Progressing | The planned programme is 37% Complete. A significant programme of unplanned diverted resources during the year |
| To progress programme development of the Insurance Risk Management Unit to reduce risk associated with insurance claims and improve programme for addressing high risk areas. | Progressing | Progressing | Progressing | Completed for 2018 |
| To progress programme of improved process for billing and collection of Development Contributions including addressing historical debtor records. | Progressing | Progressing | Progressing | Completed for 2018 |
| To continue to increase compliance with NPPR liabilities and ensure in as far as possible that all relevant charges and penalties accruing are collected. | Ongoing | Ongoing | Ongoing | Completed for 2018 |
| To further develop the Housing Loans Programme in terms of assisting applicants accessing housing solutions, working with customers in difficulty while improving collection levels for the organisation. | Ongoing | Ongoing | Progressing | Completed for 2018 |

Information and Communications Technology (ICT)

To Manage Information and Communications Technology (ICT) to ensure its ongoing relevance and input into maximise innovation in the interest of operational efficiency and citizens services

| ICT | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Agree and implement a revised business structure and strategy for ICT to meet evolving and current needs of the organisation. | ICT Training modules purchased for on-line training of staff Recruitment on-going in line with the ICT workforce plan approved in 2017 | Further recruitment completed in line with the ICT workforce Plan. | Recruitment in line with the Workforce plan has been progressed. | Recruitment in line with the Workforce plan has been progressed. |
| Ongoing review of ICT infrastructure and support services to ensure critical ICT infrastructure are up to date and meet the changing needs of the organisation. | Print audit completed to support the Managed Print tender due in Q2 | ICT security structures put in place within the IT section to manage ICT security alerts and incidents. | Tender has been prepared for a Managed Print Solution for the organisation to refresh the current MFP devices. A tender is being prepared to upgrade the core switches in the Council network | Tender procedure ongoing for print management. |
| Prepare an ICT technical strategy for the organisation’s ICT requirements as provided for in the Council’s ICT Strategy 2015 - 2019. | Local Government ICT strategy approved and an implementation plan is under development. Meetings with the 4 Dublin APAS authorities have taken place to manage the integration of ePlanning with APAS. | Rollout of File sharing solution to promote collaborative working between staff and contractors. | Expansion of File sharing solution within the organisation has continued. | Infrastructure review planned |
| Support the need for a relevant corporate intranet to facilitate internal communications and information dissemination. | Ongoing | Ongoing | Ongoing | Ongoing |
| Expand the use of Geographical Information Systems (GIS) technologies for collecting and managing spatial data to support improved services and performance development, monitoring and reporting across council activities. | Public facing pre-planning system awaiting validation and deployment. | Validation of the preplanning system complete, integration to the ICT network underway for rollout in Q3. Configuration of test system for ArcServer upgrade underway. | Configuration of ArcServer upgrade in progress | ArcServer upgrade completed. New intranet and internet GIS ready for rollout. |
| Continue to roll out the bench testing implementation and review of the Council’s Disaster Recovery and Business Continuity plans. | Business continuity plan under review. Remediation work underway based on the ICT security audit | Risk based assessment of all IT systems proceeding to cover GDPR and security. | Risk register established to cover all GDPR/security | Remedial work underway |
| Implement and support agreed Information Security guidelines to protect the organisations’ services and data from Cyber and other security related threats | Information Security committee in place and have met to review current policy and oversee the implementation of data security, availability and integrity. | Internal policies agreed by the ISC and an Incident response policy has been drawn up in the event of a Data security breach. | The information security Incident response policy has been approved by the SMT and adopted. | IT security risk register completed and plan in place. |
| Complete the requirement for Wexford County Council to move its Windows Management (Active Directory) from the national structure (A/D forest) which is hosted by the LGMA to a new standalone structure. | New domain created and over 60 users migrated. | Over 150 users moved to the new domain and further resources have been assigned for the completion of this project by Q4. | Over 200 migrations to the new domain have been completed and further resources have been assigned for the advancement of this project in Q4 2018. | 90% of PCs on Carricklawn have now been migrated. |
| Engage with the Customer Services Project in the interests of customer service, reduced cost and improved business process and efficiency. | Customer Relationship Management tool installed and workflows under development for designated business processes. | Customer service system deployed with limited services available online via the website. Implementation of Call Centre software to support the customer service unit and the handling of customer calls. | The Customer service CRM continues to be rolled out to sections to manage the customer engagement. A rollout schedule for Q4 is being developed. | Work is ongoing on implementing housing services in the CRM. |

HOUSING, COMMUNITY, LIBRARY, ARTS, EMERGENCY SERVICES AND ENVIRONMENT

LIBRARIES AND ARCHIVES

| LIBRARIES AND ARCHIVES | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Introduce Self-service technology in all libraries in 2018 thereby enhancing the quality of service available to the public. | Self-service machines procured and being installed in all 5 libraries. Full implementation by mid-May. | Complete. In place in all 5 libraries. | Complete. | Complete. |
| Expand the Right to Read literacy initiative with a focus on reading for young people as well as pre-school and primary aged children. | Spring into Story time festival held for pre-school. New mobile delivered with enhanced book stock. | 50% complete and on target. | 75% complete and on target. | Complete. |
| Continue the Decade of Centenary events including the commemoration of the centenary of the Female Suffrage, the death of John Redmond and the end of World War I. | Redmond 100 commemoration held including symposium, exhibition and schools pack. Talking History –Wexford project launched. | 50% complete and on target. | 75% complete and on target. | Complete and report submitted. |

ARTS DEPARTMENT

| ARTS DEPARTMENT | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Launch the ‘Advancing the Arts’ - Arts Plan 2018-2022 | Arts Plan was launched on 12th March 2018 by Minister Josepha Madigan. 750 hard copies printed and available to download PDF online via WCC website. | The Arts Department has begun to address the objectives of the new Arts Plan: A small Arts Festival fund was launched in March 2018. Providing work spaces for artist. The Bull Ring Mall in Wexford Town has been turned into artist studios and will be open to the public in July 2018. Initiate Public Art Bio-Diversity Action Research Project completed in May 2018. Commissioning of public art for New Ross By-Pass completion 2019. Other objectives such as expanding our arts-in-schools programme and producing a resource book for schools are being address (see below). | 11 festivals throughout county Wexford were awarded an overall total of €22,000. The Creative Hub in Bull Ring Mall was official opened on 6th September. It provides subsided spaces for artists, at the moment up to 25 artists avail of the 8 studio spaces. Following on from the completion of the Public Art Bio-Diversity Action Research Project. The Arts department has been successful selected for the Invitation to Collaboration 2019 and awarded €71.000 towards the project. Artist Caoimhe Kilfeather has been commissioned to create a piece of public art for the New Ross By-Pass | The small Arts Festival fund will be advertised again in early 2019. The Arts Department in partnership with WAC is filling up the final few spaces available in the Creative Hub to include a dance studio, community space and possible café shop. The Arts department will begin work on the Invitation to Collaboration project in January 2019. The south coast of Wexford will be the target area of the project. |
| Roll out “Music Generation” programmes in schools | Katherine Atkinson was appointed as the Music Generation Development Officer for Wexford starting 10 March 2018. Based WWETB . A call out for full time Music generation Administrator took place April 2018. Programme for schools will be announced in May/June 2018 | Plan for schools will be announced in July 2018 with roll out of programme beginning in September 2018. Musician tutor recruitment has begun as has developing partnerships both locally and nationally. Musician tutor recruitment has begun as has developing partnerships both locally and nationally. | Over a dozen schools will take part in the singing programme starting in September. The early years programme for children under 5 years will begin in October While 10 musicians have been recruited so far to develop partnerships both locally and nationally. | Over a dozen schools will take part in the singing programme starting in September. The early years programme for children under 5 years will begin in October. While 10 musicians have been recruited so far to develop partnerships both locally and nationally. |
| Continue the ‘Living Arts’ Schools Programme funded through ‘Creative Ireland’ targeting early school leavers in schools countywide. | Two new secondary schools (Ramsgrange and Selskar) took part in 10 week pilot arts programme through the ‘Living Arts’ specifically to target early school leavers. Funded through Creative Ireland Exhibition of work took in Wexford Arts centre April 2018 | Based on feedback from the pilot project regarding ‘Living Arts’ school programme funded through Creative Ireland, Ramsgrange school has been selected again to target early school leavers this will be longer term to begin in September 2018. Also through Creative Ireland funding a research project has been commissioned to create an Art in Education Resource Book for Primary School Teachers launch is aimed for 2019. | Artist Els Dietvorst will begin a 10 week project working with Ramsgrange Community School and the early school learners at the end of September. Artist Els Dietvorst and curator Karla Sanchez have begun a research project to create an Art in Education Resource book for Primary School Teachers. | Artist Els Dietvorst will begin a 10 week project working with Ramsgrange Community School and the early school learners at the end of September. Artist Els Dietvorst and curator Karla Sanchez have begun a research project to create an Art in Education Resource book for Primary School Teachers. |
| Establish a new annual film development award to support emerging indigenous film industry in County Wexford in partnership with Filmbase (Dublin) and Bodicci Film Company (Wexford). | WCC Arts office partnering with Screen Guild Directors Ireland and Bodecci Film company Wexford, in nationwide call out to directors to work with Wexford writers to shoot a short film in County Wexford in 2018. Call out took place March 2018. Film fund awarded will be €10, 000, | In June 2018 the Arts Department in association with Bodecii Film Company launched a short film fund of €10,000 to encourage directors/producers to team up with Wexford writers to create a short film based in County Wexford. | The winner of the short film fund will be announced in October 2018. | Writer Hannah McNiven, director Brian Rossey and producer Edwina Forkin were the winners of the short film fund of €10,000 in 2018. The short film will be produced in 2019 |

HOUSING

| HOUSING | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Continue the 3 year Social Housing Supply Programme 2017-2019 which aims to deliver 2,787 housing solutions to individuals and families who are unable to fund appropriate accommodation from their own resources these include, Address homelessness, Accelerate social housing, build more homes, improve the rental sector and utilise existing housing. | In Q1 2018 WCC have 246 units at various stages with Capital Approval from DHPLG. WCC continues to work with AHB’s and the Private Rental Sector to secure extra housing units. | In Q2 2018 WCC have 282 units at various stages with Capital Approval from DHPLG. WCC continues to work with AHB’s and the Private Rental Sector to secure extra housing units. | In Q3 2018 WCC have 292 units at various stages with Capital Approval from DHPLG. 10 units have recently completed construction. WCC continues to work with AHB’s and the Private Rental Sector to secure extra housing units. | In Q4 2018 WCC have 290 units at various stages with Capital Approval from DHPLG. 21 units have recently completed construction. WCC continues to work with AHB’s and the Private Rental Sector to secure extra housing units. |
| Continue the Maintenance of 4,400 social housing units across the County. | In Q1 2018 we carried out 2,731 repairs on WCC properties | In Q2 2018 we carried out 1,524 repairs on WCC properties | In Q3 2018 we carried out 2,072 repairs on WCC properties. | In Q4 2018 we carried out 2,959 repairs on WCC properties. |
| Continue to provide a range of housing grants throughout the County including funding to assist the elderly and people with disabilities to continue to live within their homes on a part funding basis under the following schemes, Housing Aid for Older People, Mobility Aids Grant Scheme, and Housing Adaptation Grants for People with a Disability. | A total of 99 grants have been approved in Q1 2018. HOP 53, MAG 37 and HGD 9. | A total of 93 grants have been approved in Q2 2018. HOP 42, MAG 40 and HGD 11. | In Q3 2018 we carried out 2,072 repairs on WCC properties. | A total of 117 grants have been approved in Q4 2018. HOP 66, MAG 43 and HGD 8. |

ENVIRONMENT

| ENVIRONMENT | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Further increase the number and the depth of environmental inspections being carried out in 2018. | Achieved Q1 | In accordance with the RMCEI Inspection Plan. | Ongoing in accordance with RMCEI Inspection Plan | Ongoing in accordance with RMCEI Inspection Plan |
| Continue noise surveys of wind farms in the county with the farms in the Castledockrell and Ballindaggin area to be surveyed. | In Progress | Underway | In progress in Q3 | In progress in Q3 & Q4/ |
| Continue the maintenance and management of Holmestown landfill to ensure EPA licence compliance as a closed facility. | Ongoing though out year. | Ongoing throughout the year. | Ongoing throughout the year | Ongoing throughout the year |
| Operate all Civic Amenity Sites and over 110 Bring Centres across the County. | Ongoing throughout year. | Ongoing | Ongoing | Ongoing |
| Continue to respond to reports of illegal dumping across the county in 2018 and establish additional Rapid Response Crews Continue the Programme of Coastal Protection works. | Ongoing recruitment of additional staff underway. | Progressing | In Progress | Completed Q4 |
| Provide extra Beach lifeguards and improved facilities and access at Carne Beach. | Due to be completed by Q2 | In place. | Completed in Q3 season now finished. | Completed in Q3 season now finished. |

COMMUNITY

| COMMUNITY | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| The Community Department will continue to manage, support and deliver the Local Authorities community function throughout the county in 2018, including Clonroche Amenity Area, Comhairle na nOG, Playground development Programme, County Wexford Pride of Place, REDZ, Burial Grounds & Traveller Interagency Group (TIG). | Procurement of the design team completed for the refurbishment of Pearse Park, New Ross and Redmond Park, Wexford Town. Design expected to commence in Q2 – 2018. Selection of Pride of Place the two Wexford County Council nominees for IPB Pride of Place competition finalised, namely; Bunclody Town and Craanford Village. Planning permission process for the development of a food hub in Bunclody, as an extension of the REDZ project in conjunction with the Town and Village Renewal project initiated. Traveller Inter agency group agreed the commissioning of a County Wexford Traveller Needs Analysis. | Design team selected. Design work commenced. Engagement of surveyors to carry out required surveying works. Engagement with organisers and community groups in preparation for judging day in July. Issues with planning application being discussed with Carlow County Council. Consultant appointed to carry out Needs Analysis. | Concept Designs and budgets received and reviewed Project Programmes agreed Final Design to commence Consultation Process to commence during Q4 Judging day held in Bunclody Town and Craanford village on July 26th . Planning Permission for Food Hub being progressed with Carlow County Council including discussions on DAC and Fire Certs. Meeting held in July with EHO. Final design and spec for equipment and layout being finalised. Project remains on track. Traveller Needs analysis completed and approved by TIG. | Clonroche Amenity Park at Construction Phase Redmond Park and New Ross Town Park redevelopment projects budget reviews for both project underway. Bunclody Town won first place in the Population category less than 2,000. Dispensation from Building Control Regulations has been received from Carlow County Council in respect of the Food Hub. Further information on the planning application and the fire cert is being processed. Project remains on track. Work on the two new walking trails is 90% complete. Review of Traveller Needs analysis by TIG - Action log formed - Additional representation to the TIG from Tusla secured. - Additional representation to the TIG from The Probation Service and Wexford County Childcare Committee sought. |
| Support the Public participation Network (PPN) and the continued development of the PPN in the County. | PPN County Membership Meeting event was held on 12th March at Riverside Park Hotel, Enniscorthy.PPN collaborated with IEN & Development Perspectives to bring a workshop on Sustainable Development Goals to Wexford. The workshop, ‘Bringing the Global Goals to Life’ involved sessions on 'localizing' the goals - i.e., developing an understanding of how these global goals are relevant and can be utilised at local level. | Wexford County Council continues to support and promote the work of the PPN in County Wexford through the employment of the PPN Support Officer, office space & facilities. The PPN is promoted in all relevant WCC literature and grant schemes e.g. Community Enhancement Scheme. WCC committed to a tablet devices allowance for PPN reps to further support their work. WCC also shares relevant information with the PPN e.g. grant schemes etc. | Two new Community and Voluntary PPN representatives elected to the LCDC. Wexford County Council continues to support and promote the work of the PPN in County Wexford through the employment of the PPN Support Officer, office space & facilities | Wexford County Council continues to support and promote the work of the PPN in County Wexford through the employment of the PPN Support Officer, office space & facilities. |
| Manage the Social Inclusion and Community Activation Programme (SICAP) 2018-2021. | Approval of the 2017 End of year annual SICAP report by the LCDC. Completion of the tendering process for the delivery of SICAP services 2018 -2022 | SICAP 2018 - 2022 commenced on 01/04/2018. The Mid-Year review was completed and approved by the LCDC in June. | Reconstitution and expansion of LCDC SICAP sub-committee to assist with the on-going monitoring and evaluation of SICAP. Engagement with Pobal, DRCD re SICAP training and programme requirements. | SICAP sub-committee site visit to Courtown to monitor and evaluate delivery of programme. 2019 SICAP Annual Plan ‘approved in principle’. Additional members with specific expertise approved onto the sub-committee. |
| Continue implementation and monitoring of the community element of the Local Economic and Community Plan (LECP). | Commenced reporting on the measurable indicators of success with a 2016 timeframe. | Work on reporting on the measurable indicators of success with a 2016 timeframe continued | Work on reporting on the measurable indicators of success with a 2016 timeframe is ongoing. HLG 1 Initiative Funding secured from Science Foundation Ireland for a Science Festival during Science Week 11 – 18 November, 2018. | Work on reporting on the measurable indicators of success with a 2016 timeframe is ongoing. HLG 1 Initiative. WexSci – Wexford Science Festival took place during Science Week from 11th to 18th November, 2018 with the assistance of funding from Science Foundation Ireland. |
| Develop a “Community Hub” in Bridgetown. | Completion of refitting works of community hub premises at Bridgetown in preparation for roll out of services in partnership with FDYS from Q2 – 2018. | Bridgetown Community Hub commenced operation. | Bridgetown Community Hub consolidated and expanded services | Community Hub consolidated and embedded into local community. |
| Develop the County Wexford Age Friendly Council. | Election of the County Wexford Older Persons Council to promote and assist with the implementation of the County Wexford Age Friendly Strategy 2017 - 2021. | Older Peoples Council Executive Committee has been established, meet and set out a work plan for the year. Cultural Companion project rolled out in conjunction with the Art Dept. | Older People’s Council and Age Friendly meetings held. Priorities identified incl. walkability audit for Templeshannon, Meals on Wheels mapping and Community Cafes. Cultural Companions initial 3 months completed successfully – great feedback and well attended. Sept to Nov scheduled completed – Volunteers to run the Meet & Greet. | Work on-going on priorities identified by the OPC. |
| Develop the Celtic Routes Interreg project as lead partner. | Liaised with Irish and Welsh partners toward development of Interreg project during 2018. Dedicated new staff member to lead project to be selected in Q2 – 2018 | Dedicated new staff member to lead project appointed. | The Mobilisation Phase has been completed. Research and Engagement Delivery Phase commenced. Mapping completed and Market Research underway | Market research contract was completed and presented. The second delivery phase is underway, “Development of Trails and Establishing Brand Values”. The first regional event was delivered. |
| Implement the Town and Village Renewal Programme. | Continued to assist successful 2017 applicants with implementation phase of Town and Village Renewal Programme, including liaising with Department on progress and reporting requirements. Assisted with capacity building, dissemination of advice for prospective applicants under the expected 2018 iteration of the Town and Village Renewal Programme. | 12 applications successfully submitted to the Department. Decision on same expect during Qtr. 3. | Completed 2017 Projected Drawdown Returns sent to Department. Decision on 2018 applications outstanding (14/09/2018) | Press Release issued Friday 5th October 2018 12 locations successful (100% applications) €1,334m granted (100% funded) Presentation Night & Workshop for Successful applicants held Tuesday the 30th October 2018 2019 Workshops held – 1 in each District Town – Gorey 4th December 2018, Wexford 6th December 2018, New Ross 11th December 2018 & Enniscorthy 13th December 2018 Health Checks, Village Teams and Village Plans being progressed in Rosslare Harbour, Bridgetown and Foulksmills. Rosslare Harbour Village Team has agreed funding spend & Public Meeting held 3rd December 2018 Bridgetown – Funding agreed on Playground – Tenders due 19th December 2018 Foulksmills – Village Team members Selected |

SPORTS ACTIVE WEXFORD (Local Sports Partnership)

| SPORTS ACTIVE | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Launch the Sports Active Wexford Strategy, delivering programmes across three themes: Empowering, Enabling Inclusion and supporting the Sports Sector. | Safeguarding Courses (Child Protection) Safeguarding 1: 2 Courses have been completed: 88 total attendance for 2018: participants Safeguarding 2: 1 Course has been competed: 34 total attendance for 2018 participants “Get Ireland Swimming” ‘Get Ireland Swimming’ is a Healthy Ireland initiate run by Swim Ireland and Ireland Active. The programme is an intervention which is giving National School students the opportunity to learn to swim or to continue their swimming development. Swim Ireland have been fortunate to develop a partnership with Sport Active Wexford (Local sports partnership) in the Get Ireland swimming Initiative here in Wexford. Swim Ireland and Sports Active Wexford are working closely with a number of schools in County Wexford, with the support of the Local community Swimming pools. The programme was launched at the new Edmund Rice Bun Scoil Ri, New Ross, where Wexford Olympian Grainne Murphy and Sports Co-ordinator Fran Ronan presented the goodie bags to the Principal Gerry Moran. Phase one of ‘Get Ireland Swimming’ is focused on increasing swimming participation amongst the National school population. This phase will see over 700 students in County Wexford provided with Swimming lessons and Swim Ireland will be providing each child with a goodie bag which will include a swimming hat and goggles to support their swimming development and provide up to 10 weeks of lessons which includes pool hire and teaching staff .We have 23 schools availing from support on this programme, and the Support of the Healthy Ireland funding will further support the funding of swim teachers. Urban Outdoor Adventure Initiatives Outdoor recreation programmes have been developed and run in disadvantaged communities, for at- risk youth groups, disadvantaged school groups and people with disability in many countries with success. There is now a growing body of evidence to suggest that outdoor adventure programme where participants interact with nature and experience new outdoor adventure sports are successful in developing confidence and skills among participants and also help young people to manage risk and encourages them to welcome challenge. Applications were invited from Local Sports Partnerships, in a competitive bid process Sports Active Wexford was awarded €44,950 for the application for Bunclody. Staff received training for the New Schools Programme and training on Teaching People with a disability. 45 swimming teachers attended the training. The Healthy Ireland funding and Swim Ireland Dormant Accounts funding has supported national schools in Wexford with a total of €26,365. Sports Active Wexford supports schools in Wexford to a total of €6,000. This has allowed 1,339 children from primary schools participate in 3 Swimming pools across Wexford in 2018 from January to March. The staffs in the Centres have been provided with training for the programme and training on Teaching Swimming to children with a disability Operation Transformation The RTE programme is on its 11th Series this January. The LSP network held their National Walks on the 13th of January. Sports Active Wexford (Local Sports Partnership) organised the National Walk from The Promenade Country Walk in Enniscorthy. Over 150 walkers of all ages took part in the 5 km walks around the county despite the yellow weather warnings. There was a great atmosphere in Enniscorthy with 50 people participating. We would like to thank our great volunteers who supported the event, Wexford County Council and Enniscorthy Municipal District and also our sponsors Pettitt's Supervalu, Aldi Enniscorthy and Lidl Enniscorthy. Coaching Children Workshop Sports Active Wexford delivered their first Coaching Children Workshops on Wednesday 10th of January to Wexford GAA Development Officers and coaching staff. Coaching Children Workshops are a new four part workshop series developed by Coaching Ireland as a non-sport-specific course for all coaches. We have run two courses in the first quarter 48 participants. Sports Chairs Sports Active has been able to secure funding for 7 Sports Chairs which will be stored in Enniscorthy and used by the Slaneyside Superstars. These chairs will also be available for use by other programmes for people with a disability, schools, or for disability awareness. This has been enabled by both the Funding from the LCDC and CYPSC healthy Ireland funds. Leadership Programme and playground markings There are currently three leadership courses running in secondary schools: Selskar College (Sports Leader 2), CBS New Ross and Kennedy College New Ross. Playground Markings are in Kiltealey NS at present and there are five schools currently on waiting list for the markings. Scooch for Mens Sheds We have run 3 tournaments in the first quarter involving over 45 men Playground Markings: Playground markings are a programme we have used to support active play in primary schools. We have purchased paint and a set of Stencils for schools at present 8 national schools have been supported. | Safeguarding 1: 11 Courses have been completed: total attendance for 2018: 165 participants Safeguarding 2:3 Courses has been competed: total attendance for 2018: 40 participants Swim For a Mile We supported two events with the Swim Ireland National Swim for a mile campaign with 34 participants in Courtown and the Apex New Ross. The Swim for a Mile relay with 54 Students from Bunscoil Ris who collectively swam over 4km in their swimming lessons at the Apex. Men’s Sheds Scooch Programme: We have now extended this programme for the coming months with support from the HSE funding. We supported the Scooch Blitz hosted by Adamstown Men’s shed, where 16 participants enjoyed a friendly morning playing this new game. Excellent engagement and plans for further competitions and programmes now going ahead. Get Active Fun Games for Preschool Children. The training programme was held for 24 staff of 12 Childcare centres, supported by Wexford County Childcare Committee. Excellent skills developed with great feedback from the groups. This programme also enabled the centres to access resources and an equipment voucher for €200. This action was undertaken under the CYPSC healthy Ireland funding. Panel of Tutors Over the past two months SAW have advertised and met with tutors and coaches from around Wexford to form a panel of tutors and coaches from which we will be able to use for different programmes around Wexford. Equipment to schools Dance mats have been to FCJ Bunclody and to Rathgarogue NS for Active school weeks. Scooch equipment has been to St. Mary’s NS, Enniscorthy for their Active School Week. Golf: A link has been made by Sports Active Wexford between St. Mary’s NS and the Pitch and Put next door to them. St. Patricks Pitch and Put will do coaching with St. Mary’s NS before the summer holidays as a trial with one class and will hope to extend this next year. Sports Leadership We have completed our Sports Leadership with Secondary Schools over the past few weeks; over 150 students have accessed the programmes we run with great results. Schools Involved are CBS New Ross, Collaiste Abain, Kennedy College, And Selskar College who have completed their Sports leader Level 2, the first qualification with have run at this level. Men’s Sheds On the 8th of May we were in John F. Kennedy Park and Arboretum with the Men’s Sheds groups from around Wexford for a walk and tour of the Arboretum with the extremely helpful staff of the Park. Special thanks to Jerry, Kevin and Ken for sharing their knowledge and expertise specifically around the area of trees and nature. Going forward the Men’s sheds hope to be able to make some resources for the park. We have also hosted a second Scooch Blitz for the Men’s Sheds with 22 Men turning up and enjoying the competition. Following this event we spoke to all the men about what they would like to do going forward and they would like more Blitz’s like this and maybe a competition at the end of the year. We also agreed to hold an event during Men’s Mental Health Week in June. The Men’s Mental Health week took place in Enniscorthy with the support of The Irish Heart Foundation and the National Men’s shed Association 40 men took part in the event which included Scooch and Walking Football, health checks and talks related to improving knowledge about health. Playground Markings are now in St. Joseph’s NS Gorey and Oylegate NS. They will be moving on to Tarahill NS and Ballymurn NS in the coming week. There are still 5 more schools on the list for this year. | Safeguarding 1: 19 Courses have been completed with a total attendance for 2018 of 304 participants. Safeguarding 2: 4 Courses have been completed with a total attendance of 52 participants. Go for Life Games The Go for Life Games were held in Dublin on the 9th of June and 9 older adults represented Wexford at these games. The 9 participants volunteered from a group of 20 older adults who have been attending Go for Life Games in Oylegate every Monday since April Active Retirement Health and Wellbeing Festival Sports Active Wexford had a stand showcasing the active retirement, go for life and men’s sheds programmes that we deliver in Whites Hotel in June at the Active Retirement Health and Wellbeing Festival. Traveller Pride SAW supported Wexford Local Development in an event in the Sports Hub in Enniscorthy to celebrate Traveller Pride. At this event there were sports games for children to participate in and also recognition and celebration for all the traveller women who participated in the Dublin Women’s Mini Marathon on the 3rd of June. Men’s Health Week SAW linked in with Irish Men’s Sheds Association to host a National Men’s Health event in Astro Active Enniscorthy. On the day there was a speaker from Men’s Sheds, from Diabetes Ireland and Get Ireland Walk. We also had a Scooch competition and an introduction to Walking Football. 50 men were present from Men’s Sheds and also Syrian men’s groups from New Ross and Enniscorthy who came with Wexford Local Development with an aim to join the Men’s Shed groups in their area. Wheelchair GAA Training The Irish Wheelchair Association came down to Wexford in June to deliver inclusive training to all the GAA Development and coaching team. SAW is working closely with Wexford GAA to ensure that GAA is accessible to everyone in Wexford. The GAA will also be delivering a Cúl Camp in Astro Active in August for Children with a Physical Disability in conjunction with The Slaneyside Super Stars. Community Coaching Programme. We have now partnered with the ETB Learning Training Initiative in Courtown Riverchapel to work with their Level 4 Group. There are 16 participants in the group and they now have embarked on Safeguarding courses and Coaching Children Courses. This programme will we hope ling a local training programme with a number of programmes to be rolled out in the Riverchapel community Complex Parkrun –Wexford In July Sports Active participated in the Johnstown parkrun held at Wexford racecourse. Parkrun is a 5Km timed run that takes place every Saturday morning at 9.30am.. A great crowd took part with a mix of runners, walkers, first timers and regulars. It was nice to see PB’s being recorded on the morning. The event was finished off with tea/coffee and biscuits in the Jockey’s room. Number of Participants: 89 Number of Volunteers: 13 Heritage Park Junior Parkrun The inaugural Heritage Park Junior Parkrun took place on Sunday 8th September. Sports Active Wexford was one of the startup funders for this event, which is Wexford’s first junior parkrun. This is a free, weekly, timed 2k walk/jog/run at 9:30am every Sunday and is open to ages 4-14 and all abilities. The event is organised entirely by volunteers. Participants : 186 in the first 2 runs Slaneyside Super Stars Summer Camp We were lucky to be part of the Slaneyside Super Stars summer camp for children with physical disabilities and their siblings/friends in AstroActive Enniscorthy on the 11th/ 12th of July. There were 12 participants with a physical disability, of which two were new to the group and 4 able-bodied participants. Activities were provided by Warrior Kids Yoga with Sarah Dunlea, Joanne Wall from the Irish Wheelchair Association,Kinetic Fitness and Sports Active Wexford. Communities Integration Fund 2018. We have been granted €5000 from this fund to support physical activities for the Integration programme. Doras Community Picnic On In July Sports Active assisted at the Doras Community Picnic in JFK Park, New Ross. The event was organised by Doras and Wexford County Council for Syrian refugees based in County Wexford. Sports Active was delighted to be part of the event Sports Active provided an activity area for young children and their mother’s and organised taster sessions with Leinster Rugby, FAI, And Wexford GAA. It was nice to see children and adults from the local community getting involved and mixing well with the refugees. At the end of the day we were provided with a taste of some Syrian music and dance from the males in the group. It was great to see so many people trying new activities and we hope that this will lead to some participants getting involved with clubs here in Wexford. Total participants: 100 Pfizer Healthy Town We attended the Pfizer healthy town meeting at the Borough Council on Tuesday 17th. We were updated on the plans for September onwards and given information regarding the town map and upcoming events. The Wexford Town Healthy Town Facebook page is gathering information for the town map. The illustrated map will showcase a sample of the wealth of health and wellbeing-related services that are available in Wexford Town. Upcoming events as part of the programme will include Walking Leader Training organised by the Irish heart foundation, schools programmes such as YPATH, schools healthy eating awards with Catherine Fulvio, Action for life, Bizzy Breaks training, workshops on mental health with Dr. Harry Barry, a cyber-bullying workshop and a running workshop with Mary Jennings. Sport Active was asked to advertise the Healthy Town Facebook page and encourage clubs and individuals in the county to provide information for the town map Belvedere Youth Services Visit In July we welcomed a group from Belvedere Youth Services, Dublin to County Wexford. The group received funding from the task force in North Inner City Dublin to undertake a two night residential in Blackwater, Co. Wexford. The group have been taking part in the “Get Ireland Swimming” Initiative facilitated by Carol Finlay, Participation Officer with Swim Ireland, since last September and before this none of the group could swim. On Tuesday the group headed for Bunclody Swimming Pool to try a taster sessions of water polo. Belvedere had 12 participants and 10 children from the local community joined in. Then, on Wednesday the group headed for Cahore Beach. The older children took part in some pier diving and the younger children took part in some boogie boarding, paddling and a bit of sandcastle building. Fun in The Sun We started our annual summer camps “Fun in the Sun” on Tuesday 7th of August and made our way to 8 different locations around the County including Riverchapel, Curracloe Beach, Enniscorthy Sports Hub, Duncannon Beach, Rosslare Recreation Centre, St.Mary’s GAA Maudlintown, Bunclody GAA grounds and Pearse Park New Ross. We worked in partnership with the Wexford GAA, FAI, Leinster Rugby, the Surf Shack Curracloe, Cricket Leinster, Golf Ireland, Shielbaggan Outdoor Adventure Centre and Wexford Parks Tennis. We had the help of the Local Training Initiative group from Courtown in Riverchapel. Sports Leadership We began our Sports Leadership programme in educational settings around the county in September. Nick Murphy (tutor) is currently working with the transition year students in Our Lady of Lourdes, New Ross, Kennedy College New Ross and Coláiste Abbain Comhairle Goes Colourful Sports Active Wexford attended the Comhairle Goes Colourful 5k run at Wexford Racecourse. This event was as a result of young people of Wexford Comhairle na nÓg selecting positive mental health as their topic to focus on at the AGM. They felt that combining physical exercise with information and awareness provision was the best way forward. Sports Active Wexford was responsible for the purchase of powder and helped out with stewarding on the day . Number Of Participants 70 | Safeguarding 1: 21 Courses have been completed with a total attendance for 2018 of 358 participants. Safeguarding 2: 4 Courses have been completed with a total attendance of 52 participants. Sports Active has been awarded the following programmes under this fund. CYPSC :- Physical Literacy Programme for Pre Schools- €5000 Physical Activity Programme for Children and Adolescents Mental Health programme. €5000 LCDC Swimming for School Programme €8000 Men’s Shed Programme €8500 Safeguarding Courses (Child Protection) Safeguarding 1: 21 Courses have been completed with a total attendance for 2018 of 358 participants. Safeguarding 2: 4 Courses have been completed with a total attendance of 52 participants. Sports Active has been awarded the following programmes under this fund. CYPSC Physical Literacy Programme for Pre Schools- €5000 Physical Activity Programme for Children and Adolescents Mental Health programme. €5000 LCDC Swimming for School Programme €8000 Men’s Shed Programme €8500 Camross ICA (Irish Country Women’s Association) Sports Active Wexford facilitated an activity session for Camross ICA. The ladies were introduced to the game of Scooch, which they were very interested in and have since requested more training on the game. Sports Active Wexford organised more training days for the ladies in October, with the aim of linking in with the transition year students from Healthy Town (Wexford) Sports Active Wexford attended the official launch in County Hall of the Pfizer Healthy Town Ireland map in Wexford. We have been supporting the setup of this programme Wexford Hurler, and this year's Healthy Town ambassador, Lee Chin led the first event, a community walk There are some more great free events taking place around the town over the 8 weeks. These events are for all ages and abilities, with different themes from heart, body, mind and nutrition. Sports Active Wexford will be attending these events and assisting in any way possible, when needed. Triona Shalloe, Roisin Walsh and Nick Murphy attended the Irish Heart Foundation’s Walking Leader Training Day at Sarsfields GAA Club on behalf of Sports Active Wexford. Sports Leadership We began our Sports Leadership programme in educational settings around the county in September. Nick Murphy (tutor) is currently working with the transition year students in Our Lady of Lourdes, New Ross, Kennedy College New Ross and Coláiste Abbain Sports Active is running four programmes at present with the following schools - Kennedy College, Our lady Of Lourdes, Adamstown, and Selskar College, with 109 TY and 5th Year students taking part in two leadership programmes. During 2017/2018 Sports Active Wexford provided the opportunity for 183 learners to develop their leadership skills through Sport Leaders qualifications and awards. This resulted in a minimum total of 995 hours of recognised volunteering and social action being delivered Playmaker Leadership for National Schools 3 Courses have been run In Taghmon National School, Tara Hill and Kilrane NS– 121 Student participants Community Coaching Programme This programme is now up and running in Courtown Riverchapel, in partnership with Waterford and Wexford ETB. – Learning Training Imitative we have 16 participants on a level 4 QQI programme and they are at present following the Coaching Children programme The students in Courtown Local Training Initiative have completed a nine week course in Community Coaching funded and supported by Sports Active Wexford. The training was facilitated by Jamie Stafford, with both theory and practical elements and provided the students with valuable skills to enable them to contribute to their community. The group will now begin a five week Stage One Course with Ben Armstrong from Leinster Rugby. Student Placement Roisin Walsh a 3rd Student in Exercise and Health Studies at Waterford Institute of Technology started a 14 week placement with Sports Active Wexfor Heritage Park Junior Parkrun The inaugural Heritage Park Junior Parkrun took place on Sunday 9th September. Sports Active Wexford was one of the startup funders for this event, which is Wexford’s first junior parkrun. Comhairle Goes Colourful Sports Active Wexford attended the Comhairle Goes Colourful 5k run at Wexford Racecourse. This event was as a result of young people of Wexford Comhairle na nÓg selecting positive mental health as their topic to focus on at the AGM. They felt that combining physical exercise with information and awareness provision was the best way forward. Sports Active Wexford was responsible for the purchase of powder and helped out with stewarding on the day. Participants: 70 Regional Sports Development Officer Meeting Triona Shalloe (Community Sports Development Officer) from Sports Active Wexford attended the Regional Local Sports Partnership (LSP) Sports Development Officer (SDO) meeting in Dungarvan, Co.Waterford. Fourteen SDO’S from nine different LSP’S met to share knowledge, best practice and brainstorm some prospective programmes. SDO’S were given a quick demonstration of Waterford Sports Partnership’s Trishaw, which was purchased from Healthy Ireland funding, before heading out for a cycle on the Waterford Greenway. From the Shed to the Community 26 men from various Men’s Sheds across Wexford met up in Raheen to participate in a Scooch blitz. Sports Active working alongside the ‘sheds’ helped to organize the event and as one man commented on how events like this can have a huge positive impact on individuals, especially in rural communities and during the winter months. At the beginning of the Men's Shed movement there was a hesitation on some of the men about taking those first steps from their home, down through the local village and meeting possibly a new group of people. Thankfully now with the profile of the Men's shed increasing, plus their value in the local community being recognized it has become easier. Now we at the next stage where with the support of the local sports partners the men are branching more out of their sheds and engaging with more men across the county. Our 2nd Men’s Shed Scooch Blitz of the season in Ballycullane hall. The blitz took place from 11am- 1pm, followed by tea & sandwiches afterwards, then the men headed to Tintern Abbey for 2pm, where they were given a guided tour of the trails and sculptures by Pat Caulfield of Tintern Abbey. The men are now set for the Inter county Blitz between Wexford, Limerick and Kildare due to take place in Kildare on Monday 19th of November. Participants: 17 Men’s Sheds Inter County Scooch Skirmish On Monday 19th of November Wexford Men’s Shed attended an Inter County Scooch Skirmish hosted by Kildare Sports Partnership in Athy, Co.Kildare. Wexford, Limerick and Kildare were represented on the day. Over 40 men participated in the event and it was a great way to celebrate International Men’s Day. Frank Fahey who is the founder of Scooch organised the day with the help of Kildare Sports Partnership and in conjunction with Healthy Ireland. Edel Byrne from Irish Men’s Sheds Association was present on the day to meet all the participants. Enniscorthy Men’s Shed has offered to host the return match in Wexford early in the New Year. European Week of Sport European week of Sport took place from the 24th - 30th of September and was a week-long celebration of sport and physical activity. National Fitness Day took place during this week on Thursday 27th of September. To celebrate this week, Sports Active Wexford organised a week full of different activities free of charge for staff members to try in County Hall and at outside venues. The activities included Circuits Class, Walking, Yoga, Zumba, Kinetic fitness and Jump fitness. There was a great response to the yoga and Zumba classes. A special thank you to Sarah Dunlea for leading the yoga class, Theresa Roche from Kinetic fitness, Lada Kotuličová from Be Fit with Lada and Jump Fitness Wexford. Total Participants: 56 Older People’s Council Executive Committee Sports Active Wexford attended the Older People’s Council Executive Committee meeting on Friday 28th of September in County Hall and spoke to the group about the link between Sports Active Wexford and Older People in the county. The activities that we provide for example Scooch and Go For Life games were mentioned along with the grants available to older adult groups such as the Go For Life grant. Wexford Business Summit 2018 Wexford Business Summit took place on 3rd of October in County Hall and Sports Active Wexford had a stall on the day. Sports Active has committed their support to this national campaign. 20×20 is a new campaign aimed at creating a measurable cultural shift in the presentation and perception of Women’s Sport in Ireland. It is a broad-based approach with three key metrics in mind to boost media coverage, attendance at key events and participation each by 20% between now and 2020. The aim of the 20×20 movement is to give increased profiling to girls and women involved in sport at all levels. We want this campaign to stimulate behavioural change to ensure that subsequent generations have female role models to emulate as athletes, coaches and referees.” Workplace Programme Exercise classes for the staff began in October and will continue up to the Christmas Holidays. Circuits take place every Monday at 5pm lead by Triona from Sports Active Wexford, lunch-time walk take place every Tuesday and Thursday at 1pm lead by Mary T from Sports Active Wexford, Yoga every Friday from 12.30 – 13.25 and 13.30 -14.25 lead by Sarah Dunlea of Sarah Dunlea Yoga. Zumba lead by Lada Kotuličová of Be Fit With Lada is on Wednesdays at lunchtime. Staff Activities Participants 98 Yoga – 35 Walk – 8 Zumba - 15 Yoga - 31 Circuits – 9 South East Radio Sports Awards The South East Radio Sports Awards will took place on Thursday 22nd November at a Gala Ball in Riverside Park Hotel, Enniscorthy. As the main sponsor of the event, Sports Active was present on the night. 55 Awards were presented across 20 sports. Cumas Sports Active Wexford attended a meeting in Cumas, New Ross with Eoin Morrissey and Kevin Deegan from Wexford GAA and Terry O’Dowd from Cumas, to discuss GAA skills sessions for the service users in Cumas. It was agreed that Kevin Deegan would begin the sessions on the week of the 17th of September. Enniscorthy Refugee Activity Programme Sports Active Wexford and Carol Finlay, Participation Officer at Swim Ireland met with Trish Barrett from WWETB (Waterford Wexford Education and Training Board) to discuss swim programmes and other activity programmes to be developed through funding from the Department of Justice. Male Refugee Swimming Lessons Sports Active Wexford has received funding from the Communities Integration Fund 2018 through the Department of Justice and Equality. Some of this funding will be spent providing swimming lessons for male refugees based in Enniscorthy. The group will begin the swimming lessons on Friday 19th of October in the Waterfront Swimming Pool in Enniscorthy and will continue for 10 weeks. Sports Active Wexford has worked in collaboration with Waterford Wexford Education and Training Board to set up these classes. A special thank you to Carol Finlay, Participation Officer at Swim Ireland who came to Wexford to meet the group and provided them with equipment. Physical Activity Programme (CAHMS) South Wexford Child and Adolescent Mental Health Service’ who were awarded a Special Commendation at the Irish Healthcare Awards night, in the category of 'Outpatient Initiative of the Year' This Programme was run in partnership with Wexford Gymnastics and Gymnastics Ireland. Wexford gets moving on COPD An Open Day will take place in Clonard Community Centre, Wexford town on Friday 30th November 2018 from 2pm – 4pm to establish a COPD peer support and exercise group for people with Chronic Obstructive Pulmonary Disease (COPD). This is collaboration between COPD Support Ireland, Sports Active Wexford and the HSE and is supported by a lottery grant from South East Community Health Care (HSE). Members of Sports Active Wexford will be available on the day to demonstrate a variety of activities. As part of the COPD peer support and exercise group, Bryan Mullett (Sports Active Wexford Tutor) will co-ordinate weekly exercise classes in Clonard Community Centre every Thursday from 12 – 1pm starting on the 6th December. Slaneyside Super Stars Sports Active Wexford delivered two children’s wheelchairs to Slaneyside Super Stars on Monday 12th of November. We received funding from Healthy Ireland towards the purchase of these chairs. Wexford Cricket Programme In partnership with Leinster Cricket and Wexford Wanderers This year's Wexford Schools Cricket Programme operated for 10 weeks This was a two week longer period than last year due to the high demand from the schools. In all 20 schools from across the county were involved, including 9 schools that were having their first experience of cricket. 1992 children took part in the programme. The feedback from all of the schools was very positive both from the teachers and the pupils. Several teachers remarked that cricket was one of the most all-inclusive games that their schools had encountered. Bunscoil Rís Edmund Rice Senior School Barntown Bunclody Central Gorey Clonroche Craanford Curracloe Glynn Kennedy Park Tagoat Kilanerin Kildavin Kilnamanagh Kilrane NS Loreto Gorey Newbawn Oylegate Piercestown St Iberius |
|  | Woodlands For Health Primary School Golf Programme | We have secured funding for a Healthy Woodland Project to be rolled out in Partnership with Get Ireland Walking, The Wexford Trails Group, Coillte and Wexford Mental Health Services. Woodlands for health is an innovative Eco Therapy programme developed by Coillte and prescribed by HSE medical professionals for adult mental health patients to engage them in forest activities to enhance their quality of life. We hope to start this programme in August Sports Active Wexford met with Maria Dunne (Women & Girls Coordinator) from Confederation of Golf in Ireland in January 2018 to discuss increasing the participation of girls and young people in the game of Golf in Wexford. It was decided to run taster sessions in schools in county Wexford. There was a massive interest in this programme with over fifty schools sending back expression of interest forms. Due to a limited number of staff and resources it was only possible to deliver 10 sessions of this in Wexford this term and we will continue to link in with the Confederation of Golf in Ireland to deliver this session to more schools on this list in the next year. The following table shows a breakdown of all schools and students who participated in this programme through March and April this year. | WOODLANDS FOR HEALTH Woodlands for Health is an innovative Eco Therapy programme developed by Coillte and prescribed by HSE medical professionals for adult mental health patients to engage them in forest activities to enhance their quality of life. We have secured a grant for this programme from Get Ireland walking and in partnership with Wexford Mental Health, Coillte, Local Link and the Wexford walking trails , we will be launching this in August at Tintern Abbey. We have over 25 participants take part in a 12 week programme . |  |

The following table shows a breakdown of all schools and students

who participated in this programme through March and April this year.

| School Name: | Number of Students participated: |
| --- | --- |
| Our Lady of Fatima National school | 52 |
| Scoil Mhuire NS | 57 |
| Kilrane NS | 58 |
| Screen NS | 154 |
| Glenbrien NS | 62 |
| St Mary’s NS | 66 |
| St Iberius NS | 54 |
| Kiltealy NS | 45 |
| Castledockrell NS | 32 |
| Bunscoil Loreto Gorey NS | 62 |

Overall in Wexford 10 Schools were visited with 642 students participating

in the school taster session. 340 girls and 302 boys took part.

FIRE SERVICE

| FIRE SERVICE | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Commence Construction of a new fire station in New-Ross. | Engaged Lead Architect | Stage 2 completion | Stage 2 completion ongoing | Stage 2 commenced |
| Mitigate fire risk in areas of Wexford County beyond a 20 minute travel time from a fire station with a Community Fire Safety Plan. | CFSP completed | Implementation | Implementation ongoing | Implementation ongoing |
| Develop a Communications Strategy for major emergency management. | ME Media Plan drafted | Presentation to SE Regional Working Group | To be signed off by Regional Steering Group | Completed |
| Officially launch and resource the ordinary fire engineering degree in the W.I.T.; | Degree passed through registrar’s office | Official ministerial launch | Degree commences on 14/09/18 with 14 students | Completed |

CIVIL DEFENCE:

| CIVIL DEFENCE | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Continue to support and provide an effective, Volunteer based, professional organisation providing support to the primary Emergency Services (Gárdaí, Ambulance Service etc.) and support at Civil/Community events throughout the County | Providing community support, providing support to the PRA’s during severe weather | Providing community support, training continues in Wexford, Gorey and New Ross | Providing community support, providing support to the PRA’s | Providing community support, training continues in Wexford, Gorey and New Ross |
| Advance the procurement of a purpose built Civil Defence Headquarters. | Produced proposal for new building, draft plans, looking at funding options | Proposed new building too expensive, looking at alternative building options | Looking at other building options | Looking at the options to purchase a second hand building |

ROADS, TRANSPORTATION, WATER SERVICES, HEALTH & SAFETY

ROADS & TRANSPORTATION

| Roads & Transportation | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Continue to facilitate and support the construction of both the New Ross Bypass and the Enniscorthy Bypass. | Providing Ongoing Support | Providing Ongoing support | Providing ongoing Support | Providing ongoing support |
| Manage and advance all strategic National and non-National road improvement projects, in particular the Oaklands Roundabout project, the Mountelliott Roundabout project, the N11 overlay project from Kyle Cross to the Newtown Road Roundabout and the R741 resurfacing project at Ardcavan. | Oaklands Roundabout & Kyle Cross have commenced. The Tender Documents for the Mountelliott Roundabout have been completed. Expect to go to tender in May. Accommodation works on the R741 resurfacing project at Ardcavan have commenced. | Oaklands Roundabout Complete A Contractor has been appointed for the Mountelliott Roundabout will start in Qtr. 3. Accommodation works on the R741 resurfacing project at Ardcavan are complete. N11 Kyle Upper Completed in Qtr. 2. Tenders received for Phase 1 Killeens to Newtown. | Oaklands roundabout Complete. Works have commenced on the Mountelliot Roundabout. N11 Kyle upper complete. Phase 1 Killeens to Newtown commenced and will be completed in Dec. Enniscorthy Southern approach awarded and should be complete in November. | Oaklands Roundabout Complete. Works are well advanced at Mountelliot Roundabout and should be complete in Qtr 1 2019. N11 Kyle Upper Complete Phase 1 Killeens to Newtown commenced and will be complete Qtr 1 2019. Enniscorthy Southern approach well advanced and should be complete by year end 2018. |
| Manage and complete the annual Restoration Improvement and Restoration Maintenance Programmes. | Ongoing, slightly behind due to adverse weather but will make up in QTR 2-4 | 60% of Restoration Improvement Complete. | 100% of the Restoration Maintenance complete, 80% of the Restoration Improvement Complete | 100% Restoration Maintenance and Restoration Improvement complete. |
| Complete the Pre-appraisal Plan for the Oilgate to Rosslare Harbour Scheme and submit final report to DIEPR. | The Project Appraisal Plan (Phase 0 – Scope and Pre-appraisal – of the TII’s Project Appraisal Guidelines) is almost complete. Expect to submit it to DTTaS in May. | Completed and Submitted. | Completed and submitted. | Completed and submitted |

| Continue to implement the MapRoad Pavement Management System including the condition rating of Regional and Local Roads. | Ongoing | Ongoing | Ongoing | Ongoing |
| --- | --- | --- | --- | --- |
| Replace at least 2,000 existing sodium lights with energy efficient LED lights as part of the Public Lighting Energy Saving programme. | To start in QTR 2. | 50% Installed to end of Q2. | 100% Complete to end of Qtr 3. | 100% complete |
| Promote all modes of transport including walking and cycling to improve the movement of people within and beyond the county. | Ongoing | Ongoing | Ongoing | Ongoing |
| Continue to deliver the Just-One-Life Programme. | Delivered 3 in QTR1 as scheduled to around 600 Secondary School Kids. | Ongoing | Ongoing | Ongoing |
| Promote Local Authority cycle awareness. | Ongoing | Ongoing | Ongoing | Ongoing |
| Continue the Road Safety Promotion campaign. | Ongoing | Ongoing | Ongoing | Ongoing |
| Adopt and implement a Policy for Advance School Warning Signs. | Under Review. | Under Review | Under Review | Under review |
| Review Adult School Warden signage and crossing points throughout the county. | Will start review of signage in QTR2 with view to securing funding for 2019. | Under Review | Under Review | Under review |
| Adopt and implement new county-wide Speed Limit Bye Laws. | Out for Public Consultation. To be adopted in QTR 2. | Adopted. Effective date 12/9/18 | Adopted. Effective date 12/9/18 | Adopted. Effective date 12.9.18 |
| Review and update the Parking Bye Laws in all four Districts. | Out for Public Consultation. To be adopted in QTR 2. | Adopted in all 4 Districts. Effective date 2/7/18 | Adopted in all 4 Municipal Districts. | Adopted in all 4 Municipal Districts. |
| Introduce Pay by Phone parking in all four Districts. | Tender Docs drawn up and sent to OGP to put out to Members on Framework. Implement in QTr2. | Contracts signed. Commencement date of Sept Expected. | Contracts signed. Go live date end of September 2018. | Contracts signed. Testing phase well advanced with Go Live date Jan2019. |
| Publish Skip Bye Laws for the county. | Out for Public Consultation. To be adopted in QTR 2. | Adopted by WCC. Effective date 2/7/18 | Adopted by WCC. Effective date 2/7/18 | Adopted by WCC. Effective date 2.7.18 |
| Adopt and Implement a Policy for the Control and Regulation of Advertising Signage on Public Roads, including removal of out-dated and redundant signage. | Under Review | Under Review | Under Review | Under Review. |

WATER SERVICES

Delivery of Water and Wastewater services

| WATER SERVICES | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Manage the Irish Water (IW) Service Level Agreement (SLA) and plan in accordance with the agreed levels and budget. | SLA Management is on-going through attendance at SLA meetings and monitoring of KPIs | SLA Management is on-going through attendance at SLA meetings and monitoring of KPIs | SLA Management is on-going through attendance at SLA meetings and monitoring of KPIs | SLA Management is on-going through attendance at SLA meetings and monitoring of KPIs |
| Monitor progress and delivery through monthly SLA and Annual Service Plan (ASP) review meetings with IW. | Tier 2 & Tier 3 Meetings held during quarter 1 to monitor progress | Tier 2 & Tier 3 Meetings held during quarter 2 to monitor progress | Tier 2 & Tier 3 Meetings held during quarter 2 to monitor progress | Tier 2 & Tier 3 Meetings held during quarter 4 to monitor progress and delivery of ASP. |
| Operate and maintain water services including water treatment plants and water main network under the SLA agreement with IW. | Operation and Maintenance in Water Services is on-going and operating at normal levels. | Operation and Maintenance in Water Services is on-going and operating at normal levels. | Operation and Maintenance in Water Services is on-going and operating at normal levels. | Operation and Maintenance in Water Services is on-going and operating at normal levels. |
| Operate and maintain wastewater services including wastewater treatment plants and sewerage networks under the SLA agreement with IW. | Operation and Maintenance in Waste water services is on-going and operating at normal levels | Operation and Maintenance in Waste water services is on-going and operating at normal levels | Operation and Maintenance in Waste water services is on-going and operating at normal levels | Operation and Maintenance in Waste water services is on-going and operating at normal levels |
| Continue testing and reporting for compliance with drinking water regulations. | On-going testing in accordance with Annual Sampling Programme | On-going testing in accordance with Annual Sampling Programme | On-going testing in accordance with Annual Sampling Programme | On-going testing in accordance with Annual Sampling Programme |
| Manage and achieve compliance with EPA licences. | Management of EPA licensed sites for IW is on-going | Management of EPA licensed sites for IW is on-going | Management of EPA licensed sites for IW is on-going | Management of EPA licensed sites for IW is on-going |
| Continue to monitor the Developer Provided Infrastructure (DPI) not currently under the remit of IW and progress the taking-in-charge of services where possible. | On-going liaison with Building Control Section to provide recommendations in relation to DPI. Energy costs for a number of DPI estates being funded by Water Services to date. | On-going liaison with Building Control Section to provide solutions in relation to DPI. | On-going liaison with Building Control Section to provide solutions in relation to DPI. | On-going liaison with Building Control Section to provide solutions in relation to DPI. New taking in charge process discussed and agreed. |

Capital Water & Wastewater Programmes

| CAPITAL WATER | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Delivery of Major infrastructure Projects in partnership with Irish Water under the SLA agreement. | Replacement resources recruited to assist with the management and progression of these projects. However a vacancy still exists which will impact on delivery of projects. | Delivery of Major Projects in partnership with IW is on-going. There is still a vacancy in Capital Water. | Delivery of Major Projects in partnership with IW is on-going. There is still a vacancy in Capital Water. | Delivery of Major Projects in partnership with IW is on-going. There is still a vacancy in Capital Water. Enniscorthy WWTP upgrade is substantially complete. |
| Delivery of Capital Programme (minor capital) in partnership with Irish Water under the SLA agreement | Works on-going on a number of minor capital projects for IW. | Works on-going on a number of minor capital projects for IW. | Works on-going on a number of minor capital projects for IW. | Works on-going on a number of minor capital projects for IW. |
| Delivery of Water Network Programmes in partnership with Irish Water under the SLA agreement (to reduce Unaccounted for Water (UFW)). | Meetings have been held with IW and WNP Contractor to progress works in Enniscorthy/Wexford & New Ross Districts. First Fix Leak repairs on-going in all Districts. | Works in progress in Enniscorthy/Wexford & New Ross Districts. First Fix Leak repairs on-going in all Districts. | Works in progress in Enniscorthy/Wexford & New Ross Districts. First Fix Leak repairs on-going in all Districts. | Works in progress in Enniscorthy/Wexford & New Ross Districts. First Fix Leak repairs on-going in all Districts. |

Rural Water programme

| RURAL WATER | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Administration of the private water well grants scheme. | Administration of grants is up to date | Administration of grants is on-going and is up to date | Administration of grants is on-going and is up to date | Administration of grants is on-going and is up to date |
| Administration and support for existing group schemes. | On-going support to all schemes as required. Contract works progressing for Backstairs and Kilanerin GWSs | On-going support to all schemes as required. Contract works at Backstairs substantially complete and at Kilanerin GWSs | On-going support to all schemes as required. Contract works at Blackstairs and Kilanerin GWSs complete. | On-going support to all schemes as required. |
| Provide administration and technical support for new group schemes. | Technical support for new schemes is on hold pending the recruitment of resource. | Technical support for new schemes is awaiting new Engineer. Position was offered and waiting on acceptance. | Technical support for new schemes is awaiting new Engineer. Position was offered and waiting on acceptance. | New Engineer joined who will provide technical support for new schemes |
| Testing and reporting on private water schemes for compliance with drinking water regulations | On-going in accordance with the Annual Sampling Programme. | On-going in accordance with the Annual Sampling Programme | On-going in accordance with the Annual Sampling Programme | On-going in accordance with the Annual Sampling Programme |

Health & Safety Section

| HEALTH & SAFETY | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Develop and co-ordinate a health and safety management system to the OHSAS 18001 standard and obtain full certification across all departments of Wexford County Council | Audit scheduled for June 26th. Training of all staff in OHSAS18001 is underway. | Audit scheduled for June 26th. All OHSAS18001 training now complete | Stage 1 audit successfully achieved with only two opportunities for improvement and no non-conformances. Stage 2 scheduled for 9th/10th October | Stage 2 audit successfully achieve on 9th and 10th October. We received 6 minor con-conformances. This means the organisation not has full certification to OHSAS18001. We are only the second LA in Ireland to achieve this across the whole organisation |
| Maintain OHSAS 18001 certification and the associated commitment to continuous improvement in all aspects of health and safety in Wexford Fire Services. | Surveillance audit is scheduled for May 3rd. All requirements are on target. | Surveillance audit resulted in one minor non-conformance. Now addressed | Full certification successfully achieved in September. Two non-conformances which are being addressed. | Surveillance audit scheduled for early 2019 |
| Review Ancillary Safety Statements for departments to ensure that they are in line with national guidelines for risk assessment and meet the requirements of the OHSAS 18001 standard | Ongoing in line with the H&S Section programme of work. All scheduled for sign of prior to 26th June OHSAS18001 audit. | Reviews completed. Awaiting sign off by Section Heads and Directors | Reviews completed. Awaiting sign off by Section Heads and Directors | Sign off now achieved for most sections. Still awaiting Environment, Machinery Yard and site specific Water Services |
| Progress health and safety improvements, in the form of specific, annual objectives and targets in all Sections/Departments. | Still awaiting submissions from some sections. Reminder to be sent out this week. | Submissions now received from all but 3 departments. Action lists under preparation | All submissions receive. Action plans developed and circulated to all departments. | Action plans now being updated and new targets set for 2019 |
| Manage and implement an internal audit programme to critically examine all aspects of health and safety performance across the Wexford County Council organisation. | New auditors are trained, an audit programme is in place and has commenced. | Audit programme now underway to target. | Audit programme now underway (slightly behind target) | Audit programme slightly behind target. Outstanding audits will be carried forward into 2019 |
| Develop Outdoor & Equipment Inspection Programmes, utilising new technologies wherever possible, to ensure that all statutory requirements are met, whilst ensuring the processes and requirements are simplified for the end user. | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work |
| Monitor accident, incident/ violence and aggression trends and implement timely and appropriate corrective and preventive actions. Ensure communication across the organisation of learning points from such incidents. | Ongoing in line with Health and Safety programme of Work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work |
| Ensure that facility management risk assessments are developed and reviewed, as required, for all properties and facilities across Wexford County Council. | Ongoing in line with Health and Safety programme of Work. Fire registers being developed for all buildings and responsible persons nominated | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work |
| Manage a health and safety training programme, in conjunction with the Training Department to ensure that all employees have the necessary qualifications for their job function, in line with legislative requirements and risk assessment | Ongoing in line with Health and Safety programme of Work. OHSAS18001 training for all staff to be rolled out by September | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work |

| Develop the Events Management programme, to facilitate due diligence and safety in all public events held on Wexford County Council properties and facilities, including the provision of training and public awareness. | Ongoing in line with Health and Safety programme of Work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work |
| --- | --- | --- | --- | --- |
| Work in conjunction with other Council Departments and local authorities to ensure that the health and safety aspects of major emergency preparedness are developed and considered by running an emergency event scenario. | To be run in conjunction with Fire Services in Q4 | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work | Ongoing and in line with the H&S Section programme of work |
| Prepare a submission in relation to Wexford Fire Services for the National Irish Safety Organisation annual safety awards. | Nearing completion. Submission date 4th May | Completed and submission sent to NISO | Completed and NISO Category 1 award achieved. Final announcement of award will be on October12th in Killarney. | Wexford Fire Services achieved best public service award and Consistent High Achiever Award for distinction and above 5 years running |